## 2026 Activities
TVET Expert Sheet – Activities Planned for 2026 (as of 15 Jul 2026)
Row | Activity / Sub-activity | Target | Unit / Indicator | Achieved | % Progress | Status | period | Comments
Output 1.2 Enhanced capacity of Agri TVET Centres at national level to provide standardised quality training in agriculture that is relevant to labour market needs and climate action, and is gender-responsive.
28 | A.1.2.1 Develop a governance model for Agri CoEs, including mechanisms to ensure their financial sustainability | 1 | 1.2.1. Number of guiding documents for sustainable Agri CoEs developed with support of the EU-funded intervention, disaggregated by type (governance model, production unit business model, trainers’ guide) | 0 | 0% | PLANNED | September 2026-2027
29 | 1.2.1.1. Contract an expertise to conduct studies (phase 1 & 2) related to current and future governance model |  | Validated expertise report |  |  | PLANNED
30 | 1.2.1.2. Develop the governance models adapted to two schools/ CoE |  | Validated governance models |  |  | PLANNED
31 | A.1.2.2 Develop an accreditation framework for Agri CoEs, to assess the excellency level of existing centres in agriculture, adapting the existing International Self-Assessment Tool for Centres of Vocational Excellence and incorporating criteria related to climate action, gender and inclusion. | 1 | Accreditation framework | 0 | 0% | PLANNED | September 2026-2027 | Discuss the feasibility as this is being developed by other stakeholders
32 | 1.2.2.1. Conduct a benchmarking study of accreditation frameworks in other agri CoEs |  |  |  |  | PLANNED
33 | 1.2.2.2. Adapt international best practices to Rwandan context and integrate climate action, gender and inclusion metris |  |  |  |  | PLANNED
34 | 1.2.2.3. Co-organize the validation workshop |  | CoE accreditation framework validated |  |  | PLANNED
35 | A.1.2.3 Develop assessment guidelines for Agri CoEs incorporating criteria related to climate action, gender and inclusion. | 1 | Assessment guidelines | 0 | 0% | IN PROGRESS
36 | 1.2.3.1. Contract a consultant to develop assessment guidelines (experiential learning model) for CoEs |  | Contract with consultant |  |  | IN PROGRESS
37 | 1.2.3.2 Develop assessment guidelines (experiential learning model) for CoEs |  | Experiential learning model |  |  | IN PROGRESS
38 | 1.2.3.3. Organize a workshop to validate the developed guidelines |  | Assessment guidelines for CoEs validated |  |  | PLANNED
39 | A.1.2.4 Develop and/or review curricula in the trades i) agriculture, ii) animal health and iii) food processing, following the CBT/CBA requirements and ensuring alignment with labour market needs and emerging/green competencies. | 3 | Curricula | 0 | 0% | IN PROGRESS
40 | 1.2.4.1. Develop Digital Learning Content/Training manuals | 2 | Drafts of digital modules |  |  | IN PROGRESS
41 | 1.2.4.2. Organize workshops to validate developed modules | 2 | Digital content modules validated |  |  | PLANNED
42 | A.1.2.5 Review curricula in the trades i) agriculture, ii) animal health and iii) food processing to ensure they are gender-responsive and inclusive. | 1 | Workshop | 0 | 0% | IN PROGRESS
43 | 1.2.5.1. Conduct curricula review/ develop module for each trade to assess the inclusion of the aspects of gender and social inclusion. | 2 | Drafts of digital modules |  |  | IN PROGRESS
44 | 1.2.5.2. Organize workshops to validate the new module | 2 | Digital content modules validated |  |  | PLANNED
45 | A.1.2.6 Develop modular short courses, including on sustainable and circular economy, gender and nutrition. | 2 | Annual set | 0 | 0% | PLANNED | From September | Delayed as it depends on Needs assessment activity (Aimable's)
46 | 1.2.6.1. Contract consultants to develop the training contents to selected topics (Digital) | 3 | 3 consultants contracted |  |  | PLANNED
47 | 1.2.6.2. Validate developed content through a workshop | 3 | 3 training contents validated |  |  | PLANNED
48 | 1.2.6.3. Conduct training to the trainers/teachers | 3 | 3 training to teachers conducted |  |  | PLANNED
49 | 1.2.6.4. Conduct training to the farmers |  | Farmers training conducted |  |  | PLANNED
50 | 1.2.6.5. Conduct training to the students |  | Students training conducted |  |  | PLANNED
51 | A.1.2.7 Develop a gender-responsive and inclusive trainers’ guide for the revised curricula. | 1 | Guideline | 0 | 0% | IN PROGRESS
52 | 1.2.7.1. Contract consultant to develop the trainer's guide |  | Trainer's guide developed |  |  | IN PROGRESS
53 | 1.2.7.2. Conduct a workshop to validate the trainer's guide |  | Trainer's guide validated |  |  | PLANNED
54 | A.1.2.8 Provide capacity-building of staff in charge of developing training and evaluation frameworks, following the CBT/CBA methodology and addressing the unique challenges/needs of women and persons with disability in the training environment. | 4 | Capacity building session | 0 | 0% | PLANNED | August up to 2027
55 | 1.2.8.1. Conduct a consultative meeting with stakeholders involved in CBT/CBA and gender and disabilities mainstreaming to discuss the focus of the training/capacity building | 1 | 1 meeting with stakeholders conducted |  |  | PLANNED
56 | 1.2.8.2. Conduct the Training of Trainers (ToT) to selected Lead trainers | 1 | 1 lead trainers training conducted |  |  | PLANNED
57 | 1.2.8.3. Conduct the Training of Trainers to selected trainers | 1 | 1 trainers training conducted |  |  | PLANNED
58 | A.1.2.9 Support the development of Recognition of Prior Learning (RPL) in agriculture, taking into account the specific skills of women and needs of persons with disability. | 3 | Workshop | 0 | 0% | PLANNED | October up to 2028
59 | 1.2.9.1. Support RTB with Technical assistance to plan/ start the process of RPL in Agriculture |  | Process of RPL in agriculture initiated |  |  | PLANNED
60 | 1.2.9.2. Co-participate in workhops/events with stakeholders for the development of RPL in agriculture | 1 | 1 workshop with stakeholders conducted |  |  | PLANNED
61 | 1.2.9.3. Co-participate in the training for RPL assessors/evaluators | 1 | 1 training for RPL assessors conducted |  |  | PLANNED
Output 1.3 Enhanced capacity of targeted Agri CoVEs to provide quality training and a conducive learning environment for their students.
63 | A.1.3.1 Set up and build capacity of an excellency committee and the development of an excellency action plan, with dedicated initiatives and frameworks in place to support women's participation, representation, and advancement in agriculture, while also integrating climate-resilient and sustainable strategies. | 2 | Excellency committee / Excellency Action Plan | 0 | 0% | PLANNED | next year | This activity depends on the accreditation framework
95 | A.1.3.6 Support the on-the-job training of Agri CoVEs’ teaching staff through training of trainers in companies, to acquire workplace relevant skills that not only meet current industry standards but also address the pressing challenges posed by climate change. | 4 | Capacity building session | 0 | 0% | PLANNED | next year | the selection will depend on how trainers will respond to this year CPD plan
96 | 1.3.6.1. Identify the companies to host the designated trainers/teachers |  | # of companies identified |  |  | PLANNED
97 | 1.3.6.2. Sign agreement with host companies and place the trainers within the companies |  | # of host companies with signed agreements and trainers successfully placed |  |  | PLANNED
98 | 1.3.6.3. Visit the trainers under on-job-training |  |  |  |  | PLANNED
| A.1.3.8 Set up, equip and support the management of a resource centre with documentary, technological and pedagogical material. |  | Ressources center | 0 | #DIV/0! | PLANNED |  | Initially planned for october, but it's moved to 2028 after confirmation of the setup of resource center

## 2026 Activities improved
TVET AGRI -Ubuhinzi Skills + Project
TVET Expert Sheet – Activities Planned for 2026 (as of 15 Jul 2026)
Row | Activity / Sub-activity | Target | Unit / Indicator | Status | period | Comments
Output 1.2 Enhanced capacity of Agri TVET Centres at national level to provide standardised quality training in agriculture that is relevant to labour market needs and climate action, and is gender-responsive.
28 | A.1.2.1 Develop a governance model for Agri CoEs, including mechanisms to ensure their financial sustainability | 1 | 1.2.1. Number of guiding documents for sustainable Agri CoEs developed with support of the EU-funded intervention, disaggregated by type (governance model, production unit business model, trainers’ guide) | PLANNED | September 2026-2027
29 | 1.2.1.1. Contract an expertise to conduct studies (phase 1 & 2) related to current and future governance model |  | Validated expertise report | PLANNED
30 | 1.2.1.2. Develop the governance models adapted to two schools/ CoE |  | Validated governance models | PLANNED
31 | A.1.2.2 Develop an accreditation framework for Agri CoEs, to assess the excellency level of existing centres in agriculture, adapting the existing International Self-Assessment Tool for Centres of Excellence and incorporating criteria related to climate action, gender and inclusion. | 1 | Accreditation framework | PLANNED | September 2026-2027 | Discuss the feasibility as this is being developed by other stakeholders
32 | 1.2.2.1. Conduct a benchmarking study of accreditation frameworks in other agri CoEs |  |  | PLANNED
33 | 1.2.2.2. Adapt international best practices to Rwandan context and integrate climate action, gender and inclusion metris |  |  | PLANNED
34 | 1.2.2.3. Co-organize the validation workshop |  | CoE accreditation framework validated | PLANNED
35 | A.1.2.3 Develop assessment guidelines for Agri CoEs incorporating criteria related to climate action, gender and inclusion. | 1 | Assessment guidelines | IN PROGRESS
36 | 1.2.3.1. Contract a consultant to develop assessment guidelines (experiential learning model) for CoEs |  | Contract with consultant | IN PROGRESS
37 | 1.2.3.2 Develop assessment guidelines (experiential learning model) for CoEs |  | Experiential learning model | IN PROGRESS
38 | 1.2.3.3. Organize a workshop to validate the developed guidelines |  | Assessment guidelines for CoEs validated | PLANNED
39 | A.1.2.4 Develop and/or review curricula in the trades i) agriculture, ii) animal health and iii) food processing, following the CBT/CBA requirements and ensuring alignment with labour market needs and emerging/green competencies. | 3 | Curricula | IN PROGRESS
40 | 1.2.4.1. Develop Digital Learning Content/Training manuals | 2 | Drafts of digital modules | IN PROGRESS
41 | 1.2.4.2. Organize workshops to validate developed modules | 2 | Digital content modules validated | PLANNED
42 | A.1.2.5 Review curricula in the trades i) agriculture, ii) animal health and iii) food processing to ensure they are gender-responsive and inclusive. | 1 | Workshop | IN PROGRESS
43 | 1.2.5.1. Conduct curricula review/ develop module for each trade to assess the inclusion of the aspects of gender and social inclusion. | 2 | Drafts of digital modules | IN PROGRESS
44 | 1.2.5.2. Organize workshops to validate the new module | 2 | Digital content modules validated | PLANNED
45 | A.1.2.6 Develop modular short courses, including on sustainable and circular economy, gender and nutrition. | 2 | Annual set | PLANNED | From September | Delayed as it depends on Needs assessment activity (Aimable's)
46 | 1.2.6.1. Contract consultants to develop the training contents to selected topics (Digital) | 3 | 3 consultants contracted | PLANNED
47 | 1.2.6.2. Validate developed content through a workshop | 3 | 3 training contents validated | PLANNED
48 | 1.2.6.3. Conduct training to the trainers/teachers | 3 | 3 training to teachers conducted | PLANNED
49 | 1.2.6.4. Conduct training to the farmers |  | Farmers training conducted | PLANNED
50 | 1.2.6.5. Conduct training to the students |  | Students training conducted | PLANNED
51 | A.1.2.7 Develop a gender-responsive and inclusive trainers’ guide for the revised curricula. | 1 | Guideline | IN PROGRESS
52 | 1.2.7.1. Contract consultant to develop the trainer's guide |  | Trainer's guide developed | IN PROGRESS
53 | 1.2.7.2. Conduct a workshop to validate the trainer's guide |  | Trainer's guide validated | PLANNED
54 | A.1.2.8 Provide capacity-building of staff in charge of developing training and evaluation frameworks, following the CBT/CBA methodology and addressing the unique challenges/needs of women and persons with disability in the training environment. | 4 | Capacity building session | PLANNED | August up to 2027
55 | 1.2.8.1. Conduct a consultative meeting with stakeholders involved in CBT/CBA and gender and disabilities mainstreaming to discuss the focus of the training/capacity building | 1 | 1 meeting with stakeholders conducted | PLANNED
56 | 1.2.8.2. Conduct the Training of Trainers (ToT) to selected Lead trainers | 1 | 1 lead trainers training conducted | PLANNED
57 | 1.2.8.3. Conduct the Training of Trainers to selected trainers | 1 | 1 trainers training conducted | PLANNED
58 | A.1.2.9 Support the development of Recognition of Prior Learning (RPL) in agriculture, taking into account the specific skills of women and needs of persons with disability. | 3 | Workshop | PLANNED | October up to 2028
59 | 1.2.9.1. Support RTB with Technical assistance to plan/ start the process of RPL in Agriculture |  | Process of RPL in agriculture initiated | PLANNED
60 | 1.2.9.2. Co-participate in workhops/events with stakeholders for the development of RPL in agriculture | 1 | 1 workshop with stakeholders conducted | PLANNED
61 | 1.2.9.3. Co-participate in the training for RPL assessors/evaluators | 1 | 1 training for RPL assessors conducted | PLANNED
Output 1.3 Enhanced capacity of targeted Agri CoEs to provide quality training and a conducive learning environment for their students.
63 | A.1.3.1 Set up and build capacity of an excellency committee and the development of an excellency action plan, with dedicated initiatives and frameworks in place to support women's participation, representation, and advancement in agriculture, while also integrating climate-resilient and sustainable strategies. | 2 | Excellency committee / Excellency Action Plan | PLANNED | next year | This activity depends on the accreditation framework
95 | A.1.3.6 Support the on-the-job training of Agri CoVEs’ teaching staff through training of trainers in companies, to acquire workplace relevant skills that not only meet current industry standards but also address the pressing challenges posed by climate change. | 4 | Capacity building session | PLANNED | next year | the selection will depend on how trainers will respond to this year CPD plan
96 | 1.3.6.1. Identify the companies to host the designated trainers/teachers |  | # of companies identified | PLANNED
97 | 1.3.6.2. Sign agreement with host companies and place the trainers within the companies |  | # of host companies with signed agreements and trainers successfully placed | PLANNED
98 | 1.3.6.3. Visit the trainers under on-job-training |  |  | PLANNED
| A.1.3.8 Set up, equip and support the management of a resource centre with documentary, technological and pedagogical material. |  | Ressources center | PLANNED |  | Initially planned for october, but it's moved to 2028 after confirmation of the setup of resource center